## Sheet1
Asset ID | Test Date | Shift | CMS
DMA-FCU-0103/0104 | 2024-04-15 | Night | Y
DMA-FCU-0105/0106 | 2024-04-15 | Night | Y
DMA-FCU-1107/1108 | 2024-04-15 | Night | Y
DMA-CEF-1101 | N/A | N/A | N
DMA-FCU-1111 | 2024-04-15 | Night | Y
DMA-FCU-0107/0108 | 2024-04-16 | Night | Y
DMA-FCU-0111/0112 | 2024-04-16 | Night | Y
DMA-FCU-0117/0118 | 2024-04-16 | Night | Y
DMA-FCU-1115 | 2024-04-17 | Night | Y
DMA-FCU-1117 | 2024-04-17 | Night | Y
DMA-FCU-1119 | 2024-04-17 | Night | Y
DMA-FCU-0115/0116 | 2024-04-18 | Night | Y
DMA-FCU-0127 | 2024-04-18 | Night | Y
DMA-FCU-1129/1130/1131/1132/1133 | 2024-04-18 | Night | Y
DMA_AHU_0101 | 2024-04-19 | Night | Y
DMA-FCU-1001 | 2024-04-19 | Night | Y
DMA-FCU-1103 | 2024-04-19 | Night | Y
DMA_AHU_1101 | 2024-04-22 | Night | Y
DMA-FCU-0121 | 2024-04-22 | Night | Y
DMA-FCU-1109/1110 | 2024-04-22 | Night | Y
DMA-FCU-1113 | 2024-04-22 | Night | Y
DMA-FCU-1121 | 2024-04-22 | Night | Y
DMA-FCU-0201/0202 | 2024-04-23 | Night | Y
DMA-FCU-1137/1138 | 2024-04-23 | Night | Y
DMA-FCU-1139/1140 | 2024-04-24 | Night | Y
DMA-FCU-1141/1142 | 2024-04-24 | Night | Y
DMA-FCU-1143/1144 | 2024-04-24 | Night | Y
DMA_AHU_1103 | 2024-04-29 | Night | Y
DMA-FCU-1145 | 2024-04-29 | Night | Y
DMA-FCU-1201/1202 | 2024-04-29 | Night | Y
DMA-FCU-0113/0114 | 2024-11-04 | Night | Y
DMA-FCU-1105 | 2024-11-04 | Night | Y
DMA-FCU-1135/1136 | 2024-11-04 | Night | Y
DMA-OAF-1105/1106 | N/A | N/A | N

## Sheet3
D
2024-04-15
2024-04-15
2024-04-15
2024-04-16
2024-04-16
2024-04-16
2024-04-18
2024-04-18
2024-04-22
2024-04-23
2024-04-23
2024-04-24
2024-04-24
2024-04-24
2024-04-29
2024-11-04
2024-11-04
341624
379626
379627
379629
379630
379633
379635
379636
379637
379639
379640
379641
379642
379643
379644
379645
384320
(1) Equipment and process interlocks not showing up for FCU units. Action SAGE
(1) Equipment and process interlocks not showing up for FCU units. Action SAGE
(1) Equipment and process interlocks not showing up for FCU units. Action SAGE
(1) Equipment and process interlocks not showing up for FCU units. Action SAGE (2) DMA_FCU_1142_PSX_01 DP sensor doesn't change value when fan runs at 100%. Action D&E/Elliots. (3) Room names shown in SCADA needs adjustments, going out of room boundary. Water balancing & flushing in progress
(1) Equipment and process interlocks not showing up for FCU units. Action SAGE (2) DMA_FCU_1144_PSX_01 DP sensor doesn't change value when fan runs at 100%. Action D&E/Elliots.
(1)Check Room code and name for all devices in Rail Lube RM room under device faceplate. Action SAGE (2) Equipment and process interlocks not showing up for FCU units. Action SAGE (3) DMA_FCU_1201_PSX_01 DP sensor doesn't change value when fan runs at Water balancing & flushing in progress
(1)Check Room code and name for DMA_FCU_1137_TEX_01 under device faceplate. Action SAGE (2) Equipment and process interlocks not showing up for FCU units. Action SAGE
(1)Check Room codes for DMA_FCU_0201_RTS_03/04/05/06 and DMA_FCU_0201_MVD_05/06 under device faceplate. Action SAGE (2) Room names shown in SCADA needs adjustments, going out of room boundary. Check if scroll bar can be removed. Action SAGE. Water balancing & flushing in progress
(1)Check Room names and codes for DMA_FCU_0117_RTS_03/04/05/06 under device faceplate. Action SAGE (2) DP sensor FCU_0117_PSX_01 not showing values. (3) FCU_0117_MVD_04 Close feedback fault. (4) FCU_0118_MCV_01 position discrepancy fault. (5) Water balancing & flushing in progress
(1)Check Room names for all devices in Mech Plt RM under device faceplate. Action SAGE (2) Equipment and process interlocks not showing up for FCU units. Action Sage
(1)Check Room names TRAC A and TRAC B should be TRAC 3 and TRAC (3) Equipment and process interlocks not showing up for FCU units. Action Sage (2) Check if TRAC 2 can be shifted to right side as per SLD, FCU_1131/32/33 should be on left side and FCU_1129/Water balancing & flushing in progress
(1)Equipment and process inetrlocks not showing up for FCU units. Action SAGE
(1)Equipment and process inetrlocks not showing up for FCU units. Action SAGE
(1)Equipment and process interlocks not showing up for FCU units. Action SAGE (2)DMA_FCU_1109_PSX_01 DP sensor reading low value when fan runs at 100%. Action Elliots/D&E (3)DMA_FCU_1110_PSX_01 DP sensor reading 330Pa(high) when fan runs at 100%. Water balancing & flushing in progress
(1)Equipment and process interlocks not showing up for FCU units. Action SAGE (2)Room name found different in device faceplate. Action SAGE
(1)Equipment and process interlocks not showing up for FCU units. Action SAGE (2)Room name found different in device faceplate. Action SAGE (3)DMA_FCU_0108_PSX_01 DP sensor reading bad quality value. Sensor missing at field. Action Elliots/D&E
(1)Fire Supp RM should be changed to BOH Corr as per single line diagram. Action CYP MOC to be raised (2)Room description needs to be changed in device faceplate panel. Action CYP MOC to be raised (3)Room names shown in SCADA needs adjustments, going out Water balancing & flushing in progress
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
DUM-DMA-FCU-0103/0104 | DMA-FCU-0103/0104 | DUM-DMA-FCU-0103/0104
DUM-DMA-FCU-0105/0106 | DMA-FCU-0105/0106 | DUM-DMA-FCU-0105/0106
DUM-DMA-FCU-0107/0108 | DMA-FCU-0107/0108 | DUM-DMA-FCU-0107/0108
DUM-DMA-FCU-0111/0112 | DMA-FCU-0111/0112 | DUM-DMA-FCU-0111/0112
DUM-DMA-FCU-0113/0114 | DMA-FCU-0113/0114 | DUM-DMA-FCU-0113/0114
DUM-DMA-FCU-0115/0116 | DMA-FCU-0115/0116 | DUM-DMA-FCU-0115/0116
DUM-DMA-FCU-0117/0118 | DMA-FCU-0117/0118 | DUM-DMA-FCU-0117/0118
DUM-DMA-FCU-0201/0202 | DMA-FCU-0201/0202 | DUM-DMA-FCU-0201/0202
DUM-DMA-FCU-1107/1108 | DMA-FCU-1107/1108 | DUM-DMA-FCU-1107/1108
DUM-DMA-FCU-1109/1110 | DMA-FCU-1109/1110 | DUM-DMA-FCU-1109/1110
DUM-DMA-FCU-1129/1130/1131/1132/1133 | DMA-FCU-1129/1130/1131/1132/1133 | DUM-DMA-FCU-1129/1130/1131/1132/1133
DUM-DMA-FCU-1135/1136 | DMA-FCU-1135/1136 | DUM-DMA-FCU-1135/1136
DUM-DMA-FCU-1137/1138 | DMA-FCU-1137/1138 | DUM-DMA-FCU-1137/1138
DUM-DMA-FCU-1139/1140 | DMA-FCU-1139/1140 | DUM-DMA-FCU-1139/1140
DUM-DMA-FCU-1141/1142 | DMA-FCU-1141/1142 | DUM-DMA-FCU-1141/1142
DUM-DMA-FCU-1143/1144 | DMA-FCU-1143/1144 | DUM-DMA-FCU-1143/1144
DUM-DMA-FCU-1201/1202 | DMA-FCU-1201/1202 | DUM-DMA-FCU-1201/1202
DUM-DMA-OAF-1105/1106 | DMA-OAF-1105/1106 | DUM-DMA-OAF-1105/1106
Dummy Tag for IO Testing DMA-FCU-0103 & DMA-FCU-0104
Dummy Tag for IO Testing DMA-FCU-0105 & DMA-FCU-0106
Dummy Tag for IO Testing DMA-FCU-0107 & DMA-FCU-0108
Dummy Tag for IO Testing DMA-FCU-0111 & DMA-FCU-0112
Dummy Tag for IO Testing DMA-FCU-0113 & DMA-FCU-0114
Dummy Tag for IO Testing DMA-FCU-0115 & DMA-FCU-0116
Dummy Tag for IO Testing DMA-FCU-0117 & DMA-FCU-0118
Dummy Tag for IO Testing DMA-FCU-0201 & DMA-FCU-0202
Dummy Tag for IO Testing DMA-FCU-1107 & DMA-FCU-1108
Dummy Tag for IO Testing DMA-FCU-1109 & DMA-FCU-1110
Dummy Tag for IO Testing DMA-FCU-1129 & DMA-FCU-1130
Dummy Tag for IO Testing DMA-FCU-1135 & DMA-FCU-1136
Dummy Tag for IO Testing DMA-FCU-1137 & DMA-FCU-1138
Dummy Tag for IO Testing DMA-FCU-1139 & DMA-FCU-1140
Dummy Tag for IO Testing DMA-FCU-1141 & DMA-FCU-1142
Dummy Tag for IO Testing DMA-FCU-1143 & DMA-FCU-1144
Dummy Tag for IO Testing DMA-FCU-1201 & DMA-FCU-1202
Fan Coil Unit (FCU) Type 1 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 1 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 1 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 1 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 1 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 1 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 10 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 11 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 2 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 2 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 2 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 2 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 2 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 2 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 2 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 2 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 2 Commissioning T&C LEVEL 2
LIC20731
LIC20731
LIC20731
LIC20731
LIC20731
LIC20731
LIC20732
LIC20732
LIC20732
LIC20732
LIC20732
LIC20732
LIC20732
LIC20732
LIC20732
LIC20740
LIC20741
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress

## Sheet2
Z
2022-04-22
2022-04-29
2024-04-15
2024-04-17
2024-04-17
2024-04-17
2024-04-18
2024-04-19
2024-04-19
2024-04-19
2024-04-19
2024-04-22
2024-04-22
2024-11-04
2024-12-04
232944
232945
232946
232952
379647
379649
379650
379651
379653
379683
379684
379685
379686
379687
379689
379690
(1) Equipment and process interlocks not showing up for FCU units. Action SAGE
(1) Equipment and process interlocks not showing up for FCU units. Action SAGE.
(1)Check Room code for all devices under device faceplate. Action SAGE (2) Equipment and process interlocks not showing up for FCU units. Action SAGE
(1)Check Room codes for devices in Store room under device faceplate. Action SAGE (2) Equipment and process interlocks not showing up for FCU units. Action SAGE
(1)Check Room codes for DMA_FCU_1121_RTS_01/02 under device faceplate. Action SAGE (2) FCU_1121_RTS_01 and 02 showing values in negative. (3) Equipment and process interlocks not showing up for FCU units. Action SAGE
(1)Check Room names and codes for DMA_FCU_0121_RTS_01 and DMA_FCU_0121_RTS_02 under device faceplate. Action SAGE (2) Equipment and process interlocks not showing up for FCU units. Action SAGE
(1)Check Room names and codes for DMA_FCU_1113_RTS_01/02 and DMA_FCU_1113_MVD_01/02 under device faceplate. Action SAGE (2) FCU_1113_TEX_01 showing 0 value (3) Equipment and process interlocks not showing up for FCU units. Action SAGE
(1)Equipment and process interlocks not showing up for FCU units. Action SAGE
(1)Equipment and process interlocks not showing up for FCU units. Action SAGE
(1)Equipment and process interlocks not showing up for FCU units. Action SAGE (2)DMA_AHU_1101_PSX_01 DP sensor reading 550Pa(high) when fan runs at 100%. Action Elliots/D&E (3)DMA_AHU_1101_PSX_02 DP sensor shows very low reading when fan runs at Awaiting Chiller
(1)Equipment and process interlocks not showing up for FCU units. Action SAGE (2)East and West room positions needs to be swapped as per single line diagram. Action SAGE (3)ECS plant 4 (801-04) should be changed to ECS plant (801-01) as per single line diagram. Awaiting Chiller
(1)Equipment and process interlocks not showing up for FCU units. Action SAGE (2)Room codes and numbers not matching with single line diagram. Action SAGE
(1)Equipment and process interlocks not showing up for FCU units. Action SAGE (2)Room name found different in device faceplate for DMA_FCU_1119_RTS_02. Action SAGE
(1)No Room name and code for DMA_FCU_1001_RTS_01 under device faceplate. Action SAGE (2) Equipment and process interlocks not showing up for FCU units. Action SAGE (3) DMA_FCU_1001_PSX_01 DP sensor doesn't change value when fan runs at 100%. Action Water balancing & flushing in progress
Air Handling Unit
Air Handling Unit
Air Handling Unit
Air Handling Unit Commissioning T&C LEVEL 2
Air Handling Unit Commissioning T&C LEVEL 2
Air Handling Unit Commissioning T&C LEVEL 2
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Anzac Station
Avaialble
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Available
Awaiting Chiller
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Complete
Cylinder Exhaust Fan
Cylinder Exhaust Fan Commissioning T&C LEVEL 2
DMA-AHU-0101
DMA-AHU-1101
DMA-AHU-1103
DMA-CEF-1101
DMA-FCU-0121
DMA-FCU-0127
DMA-FCU-1001
DMA-FCU-1103
DMA-FCU-1105
DMA-FCU-1111
DMA-FCU-1113
DMA-FCU-1115
DMA-FCU-1117
DMA-FCU-1119
DMA-FCU-1121
DMA-FCU-1145
Fan
Fan Coil Unit (FCU) Type 10 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 10 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 3 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 3 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 3 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 3 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 6 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 6 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 6 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 6 Commissioning T&C LEVEL 2
Fan Coil Unit (FCU) Type 6 Commissioning T&C LEVEL 2
Fan Coil Unit (Indoor)
Fan Coil Unit (Indoor)
Fan Coil Unit (Indoor)
Fan Coil Unit (Indoor)
Fan Coil Unit (Indoor)
Fan Coil Unit (Indoor)
Fan Coil Unit (Indoor)
Fan Coil Unit (Indoor)
Fan Coil Unit (Indoor)
Fan Coil Unit (Indoor)
Fan Coil Unit (Indoor)
LIC20733
LIC20733
LIC20733
LIC20733
LIC20736
LIC20736
LIC20736
LIC20736
LIC20736
LIC20740
LIC20740
LIC20746
LIC20746
LIC20746
LIC20749
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Night
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
Not yet Started
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
SAGE
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress
Water balancing & flushing in progress