## Overview_South
[5 empty] | Test Plan |  | Test C ases |  |  |  | Test Scripts |  |  |  | Data Point Test Cases |  |  |  |  | Test Plan | Alarm & Control Test Cases | [5 empty] | Alarm & Control Test Steps | [5 empty] | Error Logs Open (#of) |  | Start ID | Start |  |  | Finish ID | Finish |  |  | Float |  | Action Plan / Comments
Shaft | 5.2 Planned | 5.2 Achieved | 5.7 Planned | 5.7 Achieved | Status |  | No of Test Cases | Approved | Draft | Under Review | No of Test Scripts | Approved | Draft | Under Review | #of | #Exec | %Exec | #Pass | %Pass |  | #of | #Exec | %Exec | #Pass | %Pass |  | #of | #Exec | %Exec | #Pass | %Pass |  |  |  |  | Forecast | Last E&C | Var BL 4-Apr |  | Forecast | Last E&C | Var BL 4-Apr
Townhall | [14 empty] | 71 | 39 | 54.93% | 38 | 97.44% | 0 | 227 | 59 | 25.99% | 35 | 59.32% | 0 | 636 | 578 | 90.88% | 573 | 99.13% | 0 | 0 | 0 | S9.TC.A20520 | 45429 | [7 empty] | 0 | 0/19
Station Wide | [14 empty] | 47 | 35 | 74.47% | 34 | 97.14% | 0 | 84 | 33 | 39.29% | 26 | 78.79% | 0 | 636 | 578 | 90.88% | 573 | 99.13% | 0 | 0 | 0 | S9.TC.A20520 | 45429 | [7 empty] | 0 | 0
PSD |  |  |  |  | Approved | Test Plan is created Test Cases: 0 Approved, 0x Not Approved, Test Scripts: 0 Approved, 0x Not Approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | TSC_SAT_CMS_PSD | 11 | 11 | 100% | 11 | 100% | 0 | 148 | 148 | 100% | 148 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TVCS |  |  |  |  | Approved | Test Plan is created Test Cases: 0 Approved, 0x Not Approved, Test Scripts: 0 Approved, 0x Not Approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 11 | 78.57% | 11 | 100% | TSC_SAT_CMS_TVCS | 5 | 5 | 100% | 1 | 20% | 0 | 192 | 147 | 76.56% | 144 | 97.96% | 0 | 0 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0
FDS |  |  |  |  | Approved | Test Plan is created Test Cases: 0 Approved, 0x Not Approved, Test Scripts: 0 Approved, 0x Not Approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0% | 0 | - | TSC_SAT_CMS_FDS | 23 | 0 | 0% | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0
VT |  |  |  |  | Approved | Test Plan is created Test Cases: 0 Approved, 0x Not Approved, Test Scripts: 0 Approved, 0x Not Approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 100% | 3 | 100% | TSC_SAT_CMS_VT | 5 | 1 | 20% | 0 | 0% | 0 | 8 | 8 | 100% | 6 | 75% | 0 | 0 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0/160
RSG |  |  |  |  | Approved | Test Plan is created Test Cases: 7 Approved, 0x Not Approved, Test Scripts: 7 Approved, 0x Not Approved | 27 | 27 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | - | - | - | - | TSC_SAT_CMS_RSG | 1 | 0 | 0% | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0
Security, Access & Control |  |  |  |  | Approved | Test Plan is created Test Cases: 2 Approved, 0x Not Approved, Test Scripts: 2 Approved, 0x Not Approved | 23 | 23 | 0 | 0 | 2 | 2 | 0 | 0 | 3 | 0 | 0% | 0 | - | TSC_SAT_CMS_SEC | 3 | 0 | 0% | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CCTV |  |  |  |  | Approved | Test Plan is created Test Cases: 8 Approved, 0x Not Approved, Test Scripts: 8 Approved, 0x Not Approved | 9 | 9 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | - | - | - | - | TSC_SAT_CMS_CCTV | 12 | 2 | 16.67% | 1 | 50% | 0 | 23 | 12 | 52.17% | 12 | 100% | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Worklot(s): WLD/RNA/04583 (Stage 1) - PLANNED, WLD/RNA/04579 (Stage 2)- PLANNED , WLD/RNA/05384 (Stage 3)- PLANNED
Hydraulics |  |  |  |  | Approved | Test Plan is created Test Cases: 34 Approved, 23x Not Approved, Test Scripts: 34 Approved, 25x Not Approved | 63 | 40 | 23 | 0 | 59 | 34 | 3 | 22 | 8 | 8 | 100% | 7 | 87.5% | TSC_SAT_CMS_HYD | 8 | 5 | 62.5% | 5 | 100% | 0 | 111 | 111 | 100% | 111 | 100% | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electrical (BES) |  |  |  |  | Approved | Test Plan is created Test Cases: 3 Approved, 0x Not Approved, Test Scripts: 3 Approved, 0x Not Approved | 49 | 49 | 0 | 0 | 3 | 3 | 0 | 0 | 1 | 1 | 100% | 1 | 100% | TSC_SAT_CMS_LV | 2 | 1 | 50% | 1 | 100% | 0 | 21 | 21 | 100% | 21 | 100% | 0 | 0 | 0 | S9.TC.A26830 | 2023-09-18 | 2023-09-18 | - | S9.TC.A18030 | 2023-09-18 | 2023-09-18 | - | - | 0 | 0
Lighting (BES) |  |  |  |  | Approved | Test Plan is created Test Cases: 14 Approved, 0x Not Approved, Test Scripts: 14 Approved, 0x Not Approved | 20 | 20 | 0 | 0 | 14 | 14 | 0 | 0 | 3 | 3 | 100% | 3 | 100% | TSC_SAT_CMS_LTH | 3 | 0 | 0% | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 1 | 0 | S9.TC.A20330 | 2024-06-18 | 2024-06-18 | 0 | S9.TC.A20440 | 2024-06-28 | 2024-06-28 | 0 | 0 | 0 | Same log for ech station. Log linked to Test Plan so count repeats. #8262 - (RNA) - Raised in Blockade 15 [Target Close: TBC] - Assingned to Eng. -Next CMS Release MTCMS25.3.2
MVAC |  |  |  |  | Approved | Test Plan is created Test Cases: 1 Approved, 0x Not Approved, Test Scripts: 1 Approved, 0x Not Approved | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 100% | 3 | 100% | TSC_SAT_CMS_EWMS | 3 | 2 | 66.67% | 2 | 100% | 0 | 35 | 35 | 100% | 35 | 100% | 0 | 0 | 0 | S9.TC.A20530 | 2024-04-10 | 2024-04-10 | 0 | S9.TC.A26820 | 2024-04-18 | 2024-04-18 | 0 | 0 | 0 | 0
EWMS |  |  |  |  | Approved | Test Plan is created Test Cases: 0 Approved, 0x Not Approved, Test Scripts: 0 Approved, 0x Not Approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 100% | 6 | 100% | TSC_SAT_CMS_MVAC | 6 | 5 | 83.33% | 4 | 80% | 0 | 93 | 91 | 97.85% | 91 | 100% | 0 | 2 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | #8010 - (CYP) P2P Error Log [Target Close: 04/04/2025] -To be checked in P2P retest - Duplicated #8348 - (RNA) Missing VT devices and floor "B3M" from TSC Maps [Target Close: 30/04/2025]
City Square | [14 empty] | 0 | - | - | - | - | TSC_SAT_CMS_BMS_SYSTEM | 0 | 0 | - | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | TBC | 0 | [7 empty] | 0 | 0
VT |  |  |  |  | Approved | Test Plan is created Test Cases: 14 Approved, 0x Not Approved, Test Scripts: 14 Approved, 0x Not Approved | 11 | 11 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | - | - | - | - | TSC_SAT_CMS_ALARMS | 2 | 1 | 50% | 1 | 100% | 0 | 5 | 5 | 100% | 5 | 100% | 0 | 0 | 0 | S9.TC.A26890 | 2024-05-29 | 2024-05-29 | 0 | S9.TC.A26900 | 2024-06-06 | 2024-06-06 | 0 | 0 | 0 | 0
Security, Access & Control |  |  |  |  | Approved | Test Plan is created Test Cases: 2 Approved, 0x Not Approved, Test Scripts: 2 Approved, 0x Not Approved | 3 | 3 | 0 | 0 | 2 | 2 | 0 | 0 | 6 | 1 | 16.67% | 1 | 100% | 0 | 45 | 4 | 8.889% | 1 | 25% | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A26910 | 2024-05-29 | 2024-05-29 | 0 | S9.TC.A26920 | 2024-06-06 | 2024-06-06 | 0 | 0 | 0 | 0
CCTV |  |  |  |  | Approved | Test Plan is created Test Cases: 9 Approved, 0x Not Approved, Test Scripts: 9 Approved, 0x Not Approved | 9 | 9 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | - | - | - | - | TSC_CS_SAT_CMS_VT | 44 | 4 | 9.091% | 1 | 25% | 0 | - | - | - | - | - | 0 | 0 | 0 | S9.TC.A23150 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26150 | 2024-07-08 | 2024-07-08 | 0 | 0 | 0 | 0
FDS |  |  |  |  | Approved | Test Plan is Missing Test Cases: 1 Approved, 0x Not Approved, Test Scripts: 1 Approved, 0x Not Approved | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0% | 0 | - | TSC_CS_SAT_CMS_SEC | 0 | 0 | - | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A20670 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26140 | 2024-07-26 | 2024-07-26 | 0 | 0 | 0 | 0
Caverns | 2025-03-28 | [13 empty] | 1 | 1 | 100% | 1 | 100% | TSC_CS_SAT_CMS_CCTV | 0 | 0 | - | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A23180 | 45429 | [7 empty] | 0 | 0
VT |  |  |  |  | Approved | Test Plan is created Test Cases: 0 Approved, 0x Not Approved, Test Scripts: 0 Approved, 0x Not Approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0% | 0 | - | TSC_CS_SAT_CMS_FDS | 1 | 0 | 0% | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A20200 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26130 | 2024-08-27 | 2024-08-27 | 0 | 0 | 0 | 0
Security, Access & Control |  |  |  |  | Approved | Test Plan is created Test Cases: 9 Approved, 0x Not Approved, Test Scripts: 9 Approved, 2x Not Approved | 15 | 15 | 0 | 0 | 11 | 9 | 2 | 0 | 6 | 1 | 16.67% | 1 | 100% | 0 | 44 | 22 | 50% | 8 | 36.36% | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A20580 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26110 | 2024-07-23 | 2024-07-23 | 0 | 0 | 0 | 0
CCTV |  |  |  |  | Approved | Test Plan is created Test Cases: 19 Approved, 0x Not Approved, Test Scripts: 19 Approved, 0x Not Approved | 21 | 21 | 0 | 0 | 19 | 19 | 0 | 0 | 0 | - | - | - | - | TSC_CV_SAT_CMS_VT | 43 | 22 | 51.16% | 8 | 36.36% | 0 | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FDS |  |  |  |  | Approved | Test Plan is Missing Test Cases: 27 Approved, 0x Not Approved, Test Scripts: 27 Approved, 0x Not Approved | 25 | 25 | 0 | 0 | 27 | 27 | 0 | 0 | 2 | 0 | 0% | 0 | - | TSC_CV_SAT_CMS_SEC | 0 | 0 | - | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flinders Street | [14 empty] | 1 | 1 | 100% | 1 | 100% | TSC_CV_SAT_CMS_CCTV | 0 | 0 | - | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
VT |  |  |  |  | Approved | Test Plan is created Test Cases: 7 Approved, 0x Not Approved, Test Scripts: 7 Approved, 0x Not Approved | 17 | 17 | 0 | 0 | 7 | 7 | 0 | 0 | 3 | 0 | 0% | 0 | - | TSC_CV_SAT_CMS_FDS | 1 | 0 | 0% | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0
Security, Access & Control |  |  |  |  | Approved | Test Plan is created Test Cases: 1 Approved, 0x Not Approved, Test Scripts: 1 Approved, 0x Not Approved | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 6 | 1 | 16.67% | 1 | 100% | 0 | 40 | 0 | 0% | 0 | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0
CCTV |  |  |  |  | Approved | Test Plan is created Test Cases: 5 Approved, 0x Not Approved, Test Scripts: 5 Approved, 0x Not Approved | 5 | 5 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | - | - | - | - | TSC_FO_SAT_CMS_VT | 39 | 0 | 0% | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0
FDS |  |  |  |  | Approved | Test Plan is Missing Test Cases: 11 Approved, 0x Not Approved, Test Scripts: 11 Approved, 0x Not Approved | 13 | 13 | 0 | 0 | 11 | 11 | 0 | 0 | 2 | 0 | 0% | 0 | - | TSC_FO_SAT_CMS_SEC | 0 | 0 | - | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0
Fed Square | [14 empty] | 1 | 1 | 100% | 1 | 100% | TSC_FO_SAT_CMS_CCTV | 0 | 0 | - | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 2 | 0 | 0 | 0 | [7 empty] | 0 | 0
VT |  |  |  |  | Approved | Test Plan is created Test Cases: 6 Approved, 0x Not Approved, Test Scripts: 6 Approved, 0x Not Approved | 6 | 6 | 0 | 0 | 6 | 6 | 0 | 0 | 3 | 0 | 0% | 0 | - | TSC_FO_SAT_CMS_FDS | 1 | 0 | 0% | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 2 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | #7941 - CYP to fix. Tracked in CRIM-981.Schindler are implementing a hard-wired change to rectify this issue [Target Close: Mid Feb] #8282 - (RNA) Error Log [Target Close: 02/05/2025]
Security, Access & Control |  |  |  |  | Approved | Test Plan is created Test Cases: 6 Approved, 0x Not Approved, Test Scripts: 6 Approved, 0x Not Approved | 6 | 6 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | 1 | 16.67% | 1 | 100% | 0 | 14 | 0 | 0% | 0 | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0
CCTV |  |  |  |  | Approved | Test Plan is created Test Cases: 20 Approved, 0x Not Approved, Test Scripts: 20 Approved, 0x Not Approved | 28 | 28 | 0 | 0 | 28 | 20 | 0 | 0 | 0 | - | - | - | - | TSC_FS_SAT_CMS_VT | 13 | 0 | 0% | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0
FDS |  |  |  |  | Approved | Test Plan is Missing Test Cases: 8 Approved, 0x Not Approved, Test Scripts: 8 Approved, 0x Not Approved | 10 | 10 | 0 | 0 | 10 | 8 | 0 | 0 | 2 | 0 | 0% | 0 | - | TSC_FS_SAT_CMS_SEC | 0 | 0 | - | - | - | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | S9.TC.A20520 | 2024-05-17 | 2024-05-17 | 0 | S9.TC.A26120 | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0
Formulas:
Start = [1]Dashboard!AJ97
Finish ID = [1]Dashboard!AM97
Finish = [1]Dashboard!AN97

## BMS
Test Plan | Result ID | Template | Asset ID | Current Status | Steps Remaining | Additional Comments | Waiting
TSC_SAT_CMS_MVAC | 28935 | MVAC_FCU _TYPE | TSC_FCU_1401_02_FG | Deferred
TSC_SAT_CMS_MVAC | 34341 | MVAC_FCU | TSC_FCU_1401 | Passed |  | Error Log 8208
TSC_SAT_CMS_MVAC | 32804 | ACU_SYSTEM | SDU_FCU_1501_02_FG | Passed
TSC_SAT_CMS_MVAC | 32803 | ACU | SDU_FCU_1501 | Passed
TSC_SAT_CMS_MVAC | 28937 | MVAC_MOD | TSC_FCU_1401_MCV_01 | Passed
TSC_SAT_CMS_MVAC |  | AHU_SYSTEM |  | Not Executed
TSC_SAT_CMS_EWMS | 28939 | EWMS_ANA | TSC_FCU_1401_RTS_01 | Passed
TSC_SAT_CMS_EWMS | 31425 | EWMS_DIG | TSC_SDP_0106_LSH_01 | Passed
TSC_SAT_CMS_EWMS |  | PULSE_TOT |  | Not Executed
TSC_SAT_CMS_HYD | 34345 | HYD_DUTY_SELECTION | Re-Test with TEP Type Drainage | Passed
TSC_SAT_CMS_HYD | 29169 | HYD_2_STATE_INP | TSC_FCU_1401_MVD_01, TSC_FCU_1401_MVD_02 | Passed
TSC_SAT_CMS_HYD | 29166 | 2_MON_STATE_INP | TSC_FCU_1401_SMD_01 | Passed
TSC_SAT_CMS_HYD | 28998 | DRAINAGE_SYS | TSC_TEP_0301_02_FG | Passed |  | Error Logs 7485 & 7486
TSC_SAT_CMS_HYD | 31431 | VSD | TSC_SDP_0105_VSD_01 | Passed |  | Error Log 7830
TSC_SAT_CMS_HYD |  | FIR_WTR_TNK_SYS |  | Not Executed
TSC_SAT_CMS_HYD |  | DOL |  | Not Executed |  | Test after pending CR (CSD-6186)
TSC_SAT_CMS_HYD |  | FLG |  | Not Executed
TSC_SAT_CMS_LV | 32781 | LV_UPS | TSC_UPS_0412 | Passed
TSC_SAT_CMS_LTH |  | CTRL_RM_LIGHT |  | Not Executed
TSC_SAT_CMS_LTH |  | STDSTN_LIGHT |  | Not Executed
TSC_SAT_CMS_LTH |  | STDTUN_LIGHT |  | Not Executed

## VT
Test Suite | Test Case | Test Script | Last Test Cast Result | Last Test Case Execution Date | Comment
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0001 | VT_ESC | Passed | 2024-10-22 12:33
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0001 | VT_ESC_FIRE_MODES
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0002 | VT_ESC | Passed | 2024-10-22 12:19
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0002 | VT_ESC_FIRE_MODES
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0003 | VT_ESC | Passed | 2024-10-22 08:51
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0003 | VT_ESC_FIRE_MODES
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0004 | VT_ESC | Passed | 2024-10-09 08:35
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0004 | VT_ESC_FIRE_MODES
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0005 | VT_ESC | Passed | 2024-10-09 10:21
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0005 | VT_ESC_FIRE_MODES
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0006 | VT_ESC | Deferred | 2024-12-10 12:21 | PL Alarm To be Tested
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0006 | VT_ESC_FIRE_MODES
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0007 | VT_ESC | Deferred | 2024-12-10 13:08 | PL Alarm To be Tested
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0007 | VT_ESC_FIRE_MODES
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0008 | VT_ESC | Deferred | 2024-12-10 13:13 | PL Alarm To be Tested
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0008 | VT_ESC_FIRE_MODES
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0009 | VT_ESC | Deferred | 2025-02-27 08:37 | PL Alarm To be Tested
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0009 | VT_ESC_FIRE_MODES
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0010 | VT_ESC | Deferred | 2025-02-27 08:38 | PL Alarm To be Tested
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0010 | VT_ESC_FIRE_MODES
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0011 | VT_ESC | Deferred | 2025-02-27 08:38 | PL Alarm To be Tested
TSC_CV_SAT_CMS_VT_ESC | TSC_ESC_0011 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0012 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0012 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0013 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0013 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0014 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0014 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0015 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0015 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0016 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0016 | VT_ESC_FIRE_MODES
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0017 | VT_ESC
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0017 | VT_ESC_FIRE_MODES
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0018 | VT_ESC
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0018 | VT_ESC_FIRE_MODES
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0019 | VT_ESC
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0019 | VT_ESC_FIRE_MODES
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0020 | VT_ESC
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0020 | VT_ESC_FIRE_MODES
TSC_FS_SAT_CMS_VT_ESC | TSC_ESC_0021 | VT_ESC
TSC_FS_SAT_CMS_VT_ESC | TSC_ESC_0021 | VT_ESC_FIRE_MODES
TSC_FS_SAT_CMS_VT_ESC | TSC_ESC_0022 | VT_ESC
TSC_FS_SAT_CMS_VT_ESC | TSC_ESC_0022 | VT_ESC_FIRE_MODES
TSC_FS_SAT_CMS_VT_ESC | TSC_ESC_0023 | VT_ESC
TSC_FS_SAT_CMS_VT_ESC | TSC_ESC_0023 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0024 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0024 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0025 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0025 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0026 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0026 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0027 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0027 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0028 | VT_ESC | Deferred | 2025-02-20 08:51 | PL Alarm To be Tested
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0028 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0029 | VT_ESC | Deferred | 2025-02-20 08:52 | PL Alarm To be Tested
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0029 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0030 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0030 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0031 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0031 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0032 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0032 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0033 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0033 | VT_ESC_FIRE_MODES
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0034 | VT_ESC
TSC_CS_SAT_CMS_VT_ESC | TSC_ESC_0034 | VT_ESC_FIRE_MODES
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0035 | VT_ESC
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0035 | VT_ESC_FIRE_MODES
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0036 | VT_ESC
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0036 | VT_ESC_FIRE_MODES
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0037 | VT_ESC
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0037 | VT_ESC_FIRE_MODES
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0038 | VT_ESC
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0038 | VT_ESC_FIRE_MODES
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0039 | VT_ESC
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0039 | VT_ESC_FIRE_MODES
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0040 | VT_ESC
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0040 | VT_ESC_FIRE_MODES
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0041 | VT_ESC
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0041 | VT_ESC_FIRE_MODES
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0042 | VT_ESC
TSC_FO _SAT_CMS_VT_ESC | TSC_ESC_0042 | VT_ESC_FIRE_MODES
TSC_FS_SAT_CMS_VT_ESC | TSC_ESC_0043 | VT_ESC
TSC_FS_SAT_CMS_VT_ESC | TSC_ESC_0043 | VT_ESC_FIRE_MODES
TSC_FS_SAT_CMS_VT_ESC | TSC_ESC_0044 | VT_ESC
TSC_FS_SAT_CMS_VT_ESC | TSC_ESC_0044 | VT_ESC_FIRE_MODES
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0001 | VT_LIFT | Deferred | 2024-11-26 14:15 | PL Alarm To be Tested
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0001 | VT_LIFT_FIRE_MODES | Failed | 2024-11-26 14:28
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0001 | VT_LIFT_SECURE_INT
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0002 | VT_LIFT | Deferred | 2024-11-26 14:25 | PL Alarm To be Tested
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0002 | VT_LIFT_FIRE_MODES | Failed | 2024-11-26 14:35
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0002 | VT_LIFT_SECURE_INT
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0003 | VT_LIFT | Failed | 2025-03-26 | Issue with step 15. Lift state codes are incorrect and stop the lift from moving to the correct levels
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0003 | VT_LIFT_FIRE_MODES
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0003 | VT_LIFT_SECURE_INT
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0004 | VT_LIFT | Failed | 2025-03-04 09:07 | Issue with step 15. Lift state codes are incorrect and stop the lift from moving to the correct levels
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0004 | VT_LIFT_FIRE_MODES | Passed | 2025-03-04 13:04
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0004 | VT_LIFT_SECURE_INT
TSC_CS_SAT_CMS_VT_LFT | TSC_LFT_0005 | VT_LIFT
TSC_CS_SAT_CMS_VT_LFT | TSC_LFT_0005 | VT_LIFT_FIRE_MODES
TSC_CS_SAT_CMS_VT_LFT | TSC_LFT_0005 | VT_LIFT_SECURE_INT
TSC_CS_SAT_CMS_VT_LFT | TSC_LFT_0006 | VT_LIFT
TSC_CS_SAT_CMS_VT_LFT | TSC_LFT_0006 | VT_LIFT_FIRE_MODES
TSC_CS_SAT_CMS_VT_LFT | TSC_LFT_0006 | VT_LIFT_SECURE_INT
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0007 | VT_LIFT
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0007 | VT_LIFT_FIRE_MODES
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0007 | VT_LIFT_SECURE_INT
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0008 | VT_LIFT
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0008 | VT_LIFT_FIRE_MODES
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0008 | VT_LIFT_SECURE_INT
TSC_FS_SAT_CMS_VT_LFT | TSC_LFT_0009 | VT_LIFT
TSC_FS_SAT_CMS_VT_LFT | TSC_LFT_0009 | VT_LIFT_FIRE_MODES
TSC_FS_SAT_CMS_VT_LFT | TSC_LFT_0009 | VT_LIFT_SECURE_INT
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0010 | VT_LIFT
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0010 | VT_LIFT_FIRE_MODES
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0010 | VT_LIFT_SECURE_INT
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0011 | VT_LIFT
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0011 | VT_LIFT_FIRE_MODES
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0011 | VT_LIFT_SECURE_INT
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0012 | VT_LIFT | Deferred | 2025-02-21 14:14 | PL Alarm To be Tested
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0012 | VT_LIFT_FIRE_MODES | Passed | 2025-02-21 14:33
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0012 | VT_LIFT_SECURE_INT
TSC_CS_SAT_CMS_VT_LFT | TSC_LFT_0013 | VT_LIFT
TSC_CS_SAT_CMS_VT_LFT | TSC_LFT_0013 | VT_LIFT_FIRE_MODES
TSC_CS_SAT_CMS_VT_LFT | TSC_LFT_0013 | VT_LIFT_SECURE_INT
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0014 | VT_LIFT | Failed | 2025-03-18 12:50 | PL Alarm To be Tested
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0014 | VT_LIFT_FIRE_MODES | Passed | 2025-03-18 12:30
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0014 | VT_LIFT_SECURE_INT
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0015 | VT_LIFT
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0015 | VT_LIFT_FIRE_MODES
TSC_FO_SAT_CMS_VT_LFT | TSC_LFT_0015 | VT_LIFT_SECURE_INT
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0016 | VT_LIFT |  |  | Fed Square
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0016 | VT_LIFT_FIRE_MODES |  |  | Fed Square
TSC_CV_SAT_CMS_VT_LFT | TSC_LFT_0016 | VT_LIFT_SECURE_INT
TSC_CS_SAT_CMS_VT_LFT | TSC_LFT_0017 | VT_LIFT | Deferred | 2025-03-21 09:51
TSC_CS_SAT_CMS_VT_LFT | TSC_LFT_0017 | VT_LIFT_FIRE_MODES | Passed | 2025-03-21 09:55
TSC_CS_SAT_CMS_VT_LFT | TSC_LFT_0017 | VT_LIFT_SECURE_INT

## CCTV&Security
CCTV P2P
0 | Total | Caverns | City Square | Fed Square | Flinders OSD | LFT | Comments/Notes
Total cameras in CMS | 526 | 183 | 139 | 54 | 116 | 34
Cameras added in Genetec (CMS ones) | 141 | 130 | 11 | 0 | 0 | 0
Cameras Tested | 141 | 130 | 11 | 0 | 0 | 0
Passed | 141 | 130 | 11 | 0 | 0 | 0
Failed | 0 | 0 | 0 | 0 | 0 | 0
Security | [6 empty] | More information required before this site can be accurately planned to this detail

## Layouts
LV Testing Summary
LV Type | Total | Tested | Passed | Failed | Comment
UPS | 4 | 0 | 0 | 0
VT Testing Summary
VT Type | Total | Tested | Passed | Failed | Comment
Escalators | 44 | 42 | 33 | 9 | 1. ESC0030 - ESC0034 No label on B1M floor? 2. ESC21-23 Should go to B3M. B3M has not been created in CMS. 3. Escalator visuals no shown properly for ESC0006 - ESC0011.
Lifts | 17 | 17 | 16 | 1 | 1. Re-order levels. Swap order of B1M -> B1 2. LFT0015 Icon is missing on GM.
CCTV Testing Summary
CCTV | Total | Tested | Passed | Failed | Comment
CCTV | 526 | 0 | 0 | 0