## Current Status
Site | ELM Drawing | CYP Acceptance | RNA Provided Drawing | RNA Ready for Test | RNA Tested | Result
Arden | 2025-02-14 | 2025-02-19 | 2025-02-14 | 2025-03-11 | 2025-03-25
Parkville | 2025-02-28 | 2025-03-05 | 2025-02-28 | 2025-03-11 | 2025-03-25
Anzac | 2025-03-07 | 2025-03-12 | 2025-03-07 | 2025-03-31 | 2025-04-14
Franklin West | 2025-02-28 | 2025-03-05 | 2025-02-28 | 2025-03-11 | 2025-03-25
CBDN Caverns | 2025-02-28 | 2025-03-05 | 2025-02-28 | 2025-03-11 | 2025-03-25
Little LaTrobe | 2025-02-28 | 2025-03-05 | 2025-02-28 | 2025-03-11 | 2025-03-25
Franklin East
A'Beckett
LaTrobe
CBDS Caverns | 2025-04-01 | 2025-04-06 | 2025-04-01 | 2025-04-22
Flinders OSD
City Square
Fed Square
Formulas:
CYP Acceptance = IF(ISBLANK([ELM Drawing]), "", [ELM Drawing] + 5)
RNA Provided Drawing = IF(ISBLANK([ELM Drawing]), "", [ELM Drawing] )
RNA Ready for Test = IF([RNA Provided Drawing] = "", "", IF(SUMPRODUCT(--('CMS Releases'!$B2:B8 > [RNA Provided Drawing] + 10)) > 0, INDEX('CMS Releases'!$B2:B8, MATCH(TRUE, 'CMS Releases'!$B2:B8 > [RNA Provided Drawing] + 10, 0)), ""))
RNA Tested = IF(ISBLANK([RNA Ready for Test]), "", [RNA Ready for Test] + 14)
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Talk to Devin

## CMS Releases
CMS Release | Deployment date
MTCMS_250201 | 2025-02-19
MTCMS_250301 | 2025-03-11
MTCMS_250302 | 2025-03-31
MTCMS_250401 | 2025-04-22
MTCMS_250501 | 2025-05-12
MTCMS_250502 | 2025-06-02
MTCMS_250601 | 2025-06-23