## Roster (hidden)
CMS T&C
TEAM ROSTER
Column1 | NAME | Column2 | POSITION | EMAIL | PHONE

## Calendar
CMS T&C | [8 empty] | 45413
SCHEDULE CALENDAR |  |  |  |  | May | 2024
SUN | MON | TUE | WED | THUR | FRI | SAT | LEGEND
2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 |  | SCHEDULED
TENTATIVE
2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 |  | COMPLETED
CANCELLED
2024-05-12 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-18
2024-05-19 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-25
AEN - Lift Intercom Testing DMA - CYP Fire Matrix Testing PKV - CMS-FDS Issue Rectification Works
2024-05-26 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01
| SDU - CMS-SACS Testing Metrol Induction PKV - CYP Fire Matrix Testing | SDU - CMS-SACS Testing PKV - CYP Fire Matrix Testing | SDU - CMS-SACS Testing PKV - CYP Fire Matrix Testing | SDU - CMS-SACS Testing PAE&PDM - CMS-VT Retesting PKV - CYP Fire Matrix Testing | DMA - CMS-RSG (PSD - PIDS) Retest PKV - CYP Fire Matrix Testing
2024-06-02 |  | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04
0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0

## Schedule
CMS T&C
Testing Activities
DATE | EVENT | SITE | STATUS | REMARKS
2024-05-24 | AEN - Lift Intercom Testing | Arden Station | Scheduled
2024-05-24 | DMA - CYP Fire Matrix Testing | Anzac Station | Scheduled | Nights
2024-05-27 | SDU - CMS-SACS Testing | Tunnel (PAE-PKV) | Scheduled
2024-05-27 | Metrol Induction | Metrol | Scheduled
2024-05-28 | SDU - CMS-SACS Testing | Tunnel (PVK-DMN) | Scheduled
2024-05-29 | SDU - CMS-SACS Testing | Tunnel (DMN-PDM) | Scheduled
2024-05-30 | SDU - CMS-SACS Testing | Tunnel (TBC) | Scheduled | This day is only booked as contingency for tests
2024-05-30 | PAE&PDM - CMS-VT Retesting | PAE & PDM | Scheduled | West in the morning and East in the afternoon. This will also be pending issue resolution on the CYP side
2024-05-31 | DMA - CMS-RSG (PSD - PIDS) Retest | Anzac Station | Scheduled
2024-05-27 | PKV - CYP Fire Matrix Testing | Parkville Station | Scheduled | Nights
2024-05-28 | PKV - CYP Fire Matrix Testing | Parkville Station | Scheduled | Nights
2024-05-29 | PKV - CYP Fire Matrix Testing | Parkville Station | Scheduled | Nights
2024-05-30 | PKV - CYP Fire Matrix Testing | Parkville Station | Scheduled | Nights
2024-05-31 | PKV - CYP Fire Matrix Testing | Parkville Station | Scheduled | Nights
2024-06-03 | PKV - CYP Fire Matrix Testing | Parkville Station | Scheduled | Nights
2024-06-04 | PKV - CYP Fire Matrix Testing | Parkville Station | Scheduled | Nights
2024-06-05 | PKV - CYP Fire Matrix Testing | Parkville Station | Scheduled | Nights
2024-06-06 | PKV - CYP Fire Matrix Testing | Parkville Station | Scheduled | Nights
2024-06-07 | PKV - CYP Fire Matrix Testing | Parkville Station | Scheduled | Nights
2024-06-03 | Integration Testing (Intrusion) | Arden, Parkville, Metrol | Scheduled | Need to book resources for this one
2024-06-04 | Integration Testing (Intrusion) | Arden, Parkville, Metrol | Scheduled | Need to book resources for this one
2024-06-05 | Integration Testing (Intrusion) | Arden, Parkville, Metrol | Scheduled | Need to book resources for this one
2024-05-24 | PKV - CMS-FDS Issue Rectification Works | Parkville Station | Scheduled
2024-06-11 | PKV - Public Access Day (No Testing) | Parkville Station | Scheduled