## 26.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-26 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | Anzac |  |  | SHIFT FINISH TIME |  |  |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-26 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-26 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-26 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | State Library |  | Synertec | 8:00
Kabir Chhabra |  | Anzac |  | RNA | 8:00
Emilio Ito |  | 628 Bourke Street/Anzac |  | Mescada | 8:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 9:00
Nigin Balakrishnan |  | Sick |  | Mescada | [8 empty] | Sick leave
Fadi Duqman |  | Anzac/Arden |  | RNA | 8:00
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-26 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 25.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-25 |  |  | SHIFT START TIME |  | 6:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | Parkville |  |  | SHIFT FINISH TIME |  | 14:00 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-25 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-25 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-25 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-25 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 23.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-23 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | Anzac |  |  | SHIFT FINISH TIME |  | 16:30 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-23 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-23 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-23 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  |  |  | Synertec | 8:00 |  | 16:00
Kabir Chhabra |  |  |  | RNA | 8:00 |  | 16:00
Emilio Ito |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 9:00 |  | 16:30
Nigin Balakrishnan |  | Anzac |  | Mescada | 8:30 |  | 16:30
Fadi Duqman |  |  |  | RNA | 8:00 |  | 16:00
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-23 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 22.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-22 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | Anzac |  |  | SHIFT FINISH TIME |  | 17:00 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-22 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-22 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-22 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | Anzac |  | Synertec | 8:00 |  | 16:00
Emilio Ito |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 9:00 |  | 16:30
Nigin Balakrishnan |  | 628 Bourke Street |  | Mescada | 8:30 |  | 16:30
Fadi Duqman |  | Anzac |  | RNA | 8:00 |  | 16:30
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-22 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 21.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-21 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | Anzac |  |  | SHIFT FINISH TIME |  | 17:40 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-21 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-21 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-21 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | Anzac |  | Synertec | 8:00 |  | 16:00
Kabir Chhabra |  | Anzac |  | RNA | 8:00 |  | 16:00
Emilio Ito |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 9:00 |  | 16:30
Nigin Balakrishnan |  | 628 Bourke Street |  | Mescada | 8:30 |  | 16:30
Fadi Duqman |  | Arden/Parkville |  | RNA | 8:00 |  | 17:00
Arjhun Shivakumar |  | Arden/Parkville |  | Synertec | 8:00 |  | 8:00
Johanne Silvashields |  | Arden/Parkville |  | Synertec | 8:00 |  | 8:00
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-21 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 20.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-20 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | State Library |  |  | SHIFT FINISH TIME |  | 17:00 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-20 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-20 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-20 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | State Library |  | Synertec | 8:00 |  | 16:00
Kabir Chhabra |  | Anzac |  | RNA | 8:00 |  | 16:00
Emilio Ito |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 9:00 |  | 16:30
Nigin Balakrishnan |  | Anzac |  | Mescada | 8:30 |  | 16:30
Fadi Duqman |  | State Library |  | RNA | 8:00 |  | 16:30
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-20 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 19.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-19 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | Anzac |  |  | SHIFT FINISH TIME |  | 16:30 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-19 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-19 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-19 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  |  |  | Synertec | 8:00 |  | 16:00
Kabir Chhabra |  |  |  | RNA | 8:00 |  | 16:00
Emilio Ito |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 9:00 |  | 16:30
Nigin Balakrishnan |  | Anzac |  | Mescada | 8:30 |  | 16:30
Fadi Duqman |  |  |  | RNA | 8:00 |  | 16:00
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-19 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 16.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-16 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | Anzac/Parkville |  |  | SHIFT FINISH TIME |  | 16:00 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-16 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-16 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-16 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | Anzac |  | Synertec | 8:00 |  | 16:00
Kabir Chhabra |  | 628 Bourke Street |  | RNA | 8:00 |  | 16:00
Emilio Ito |  | Parkville |  | Mescada | 8:00 |  | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 9:00 |  | 16:30
Nigin Balakrishnan |  | Anzac |  | Mescada | 8:30 |  | 16:30
Fadi Duqman |  | Anzac |  | RNA | 8:00 |  | 8:00
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-16 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 15.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-15 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | 628 Bourke Street/Parkville/Town Hall |  |  | SHIFT FINISH TIME |  | 18:15 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-15 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-15 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-15 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | Anzac |  | Synertec | 8:00 |  | 16:00
Kabir Chhabra |  |  |  | RNA | [8 empty] | Currently has Thursdays for uni
Emilio Ito |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Vivek Gupta |  | Anzac |  | Mescada | 8:00 |  | 16:00
Nigin Balakrishnan |  | Anzac |  | Mescada | 8:00 |  | 16:00
Fadi Duqman |  | Anzac |  | RNA | 8:00 |  | 16:00
Harshil |  | Anzac |  | Anzac | 8:00 |  | 16:00 | [5 empty] | CYP Paid for resource
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-15 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 14.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-14 |  |  | SHIFT START TIME |  | 7:30 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | 628 Bourke Street/Metrol |  |  | SHIFT FINISH TIME |  | 16:00 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-14 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-14 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-14 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | Anzac |  | Synertec | 8:00 |  | 16:00
Kabir Chhabra |  |  |  | RNA | [8 empty] | Uni Commitments
Emilio Ito |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Nigin Balakrishnan |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Fadi Duqman |  | Anzac |  | RNA | 8:00 |  | 16:00
Harshil |  | Anzac |  | Anzac | 8:00 |  | 16:00 | [5 empty] | CYP Paid for resource For OCS
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-14 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 13.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-13 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | 628 Bourke Street/Metrol |  |  | SHIFT FINISH TIME |  | 16:30 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-13 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-13 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-13 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | Anzac/State Library |  | Synertec | 8:00 |  | 16:00
Kabir Chhabra |  | Anzac |  | RNA | 8:00 |  | 16:00 | [5 empty] | Currently has Thursdays for uni
Emilio Ito |  | Anzac |  | Mescada | 8:00 |  | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Nigin Balakrishnan |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Fadi Duqman |  | Anzac |  | RNA | 8:00 |  | 16:00
Harshil |  | Anzac |  | Anzac | 8:00 |  | 16:00 | [5 empty] | CYP Paid for resource
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-13 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 12.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-12 |  |  | SHIFT START TIME |  | 7:30 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | 628 Bourke Street/Metrol |  |  | SHIFT FINISH TIME |  | 16:00 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-12 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-12 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-12 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | Anzac |  | Synertec | 8:00 | 24:00 | 16:00
Kabir Chhabra |  | 628 Bourke Street |  | RNA | 8:00 |  | 16:00 | [5 empty] | Currently has Thursdays for uni
Emilio Ito |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Nigin Balakrishnan |  | Anzac |  | Mescada | 9:45 |  | 16:00
Fadi Duqman |  | Anzac |  | RNA | 8:00 |  | 16:00
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-12 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 09.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-09 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | Anzac/Parkville |  |  | SHIFT FINISH TIME |  | 17:00 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-09 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-09 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-09 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | Anzac |  | Synertec | 8:00 | 24:00 | 16:00
Kabir Chhabra |  | 628 Bourke Street |  | RNA | 8:00 |  | 16:00 | [5 empty] | Currently has Thursdays for uni
Emilio Ito |  | 628 Bourke Street |  | Mescada | 8:00 |  | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 8:30 |  | 16:00
Nigin Balakrishnan |  | Anzac |  | Mescada | 8:30 |  | 16:30
Fadi Duqman |  | Anzac |  | RNA | 8:00 |  | 16:00
CYP Paid for resource
CYP Paid for resource
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-09 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 08.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-08 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | Anzac/Arden/Parkville |  |  | SHIFT FINISH TIME |  | 17:00 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-08 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-08 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-08 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START |  | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | Anzac |  | Synertec | 8:00 |  | 16:00
Kabir Chhabra |  |  |  | RNA | [8 empty] | Currently has Thursdays for uni
Emilio Ito |  | Arden |  | Mescada | 8:00 |  | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 8:30 |  | 16:00
Nigin Balakrishnan |  | Anzac |  | Mescada | 8:30 |  | 16:30
Fadi Duqman |  | Parkville |  | RNA | 8:00 |  | 16:00
Harshil |  | Arden |  | ELM JV | 8:00 |  | 15:30 | [5 empty] | CYP Paid for resource
Rory |  | PArkville |  | ELM JV | 8:00 |  | 15:30 | [5 empty] | CYP Paid for resource
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-08 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 07.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-07 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | Anzac |  |  | SHIFT FINISH TIME |  | 16:30 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-07 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-07 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-07 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | State Library |  | Synertec | 8:00 | 12:00 | 16:00
Kabir Chhabra |  | Anzac |  | RNA | 8:30 | 12:00 | 15:45
Emilio Ito |  | 628 Bourke Street |  | Mescada | 8:00 | 12:00 | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 8:30 | 12:00 | 16:00
Nigin Balakrishnan |  | Anzac |  | Mescada | 11:00 | 12:00 | 16:30
Fadi Duqman |  | Anzac |  | RNA | 8:00 | 12:00 | 17:00
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-07 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 06.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-06 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | Anzac |  |  | SHIFT FINISH TIME |  | 17:00 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-06 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-06 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-06 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | Anzac |  | Synertec | 8:00 | 12:00 | 16:00
Kabir Chhabra |  | 628 Bourke Street |  | RNA | 8:00 | 12:00 | 16:00
Emilio Ito |  | Anzac |  | Mescada | 8:00 | 12:00 | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 8:00 | 12:00 | 16:00
Nigin Balakrishnan |  | Anzac |  | Mescada | 8:00 | 12:00 | 16:00
Fadi Duqman |  | Anzac |  | RNA | 8:00 | 12:00 | 16:00
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-06 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete

## 05.08.2024
DAILY RECORD SHEET
SUPERVISOR NAME |  |  | DATE | 2024-08-05 |  |  | SHIFT START TIME |  | 7:00 |  | WEATHER
ENGINEER NAME | Kai Longley |  | WORK LOCATION | Parkville |  |  | SHIFT FINISH TIME |  | 18:15 |  | TEMP MIN / MAX
SHIFT SUMMARY [general record of works, inspections] | [6 empty] | SAFETY / QUALITY |  | N/A
[7 empty] | ENVIRO / COMMS |  | N/A
[7 empty] | DELAYS TO WORKS |  | N/A
[7 empty] | PRODUCTIVITY | [6 empty] | Cost code | Cost Type | Tranx Date | Delivery Docket | Vendor | Quantity | Units | Rates | Delivery Amount | Operator Name | Description
[7 empty] | ITEM |  | DESCRIPTION |  | TARGET | ACHIEVED | NOTES / COMMENTS
[7 empty] | Productivity_1 | [6 empty] | #REF! | Productivity_1 | 2024-08-05 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_2 | [6 empty] | #REF! | Productivity_2 | 2024-08-05 |  |  | 0 |  |  |  |  | 0
[7 empty] | Productivity_3 | [6 empty] | #REF! | Productivity_3 | 2024-08-05 |  |  | 0 |  |  |  |  | 0
LABOUR
NAME |  | SITE |  | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Rates / Subcontract ] | CREW NO. | COST CODE | NOTES / COMMENTS
Chris Lawson |  | Parkville |  | Synertec | 8:00 | 12:00 | 17:00
Kabir Chhabra |  | Parkville |  | RNA | 8:00 | 12:00 | 17:00
Emilio Ito |  | 628 Bourke Street |  | Mescada | 8:00 | 12:00 | 16:00
Vivek Gupta |  | 628 Bourke Street |  | Mescada | 8:00 | 12:00 | 16:00
Nigin Balakrishnan |  | 628 Bourke Street |  | Mescada | 8:00 | 12:00 | 16:00
Fadi Duqman |  | WFH |  | RNA | 8:00 | 12:00 | 16:00
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
[14 empty] | 0 | 0010 - Labour | 2024-08-05 | 0 | 0 | 0 | hr | 85 | 0 | 0 | -
PLANT (incl small plant)
PLANT DESCRIPTION | ATTACHMENTS / EXTRAS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | HIRE ARRANGEMENT [ Wet / Dry ] | CREW NO. | COST CODE | NOTES / COMMENTS [internal float, off hired, used by others etc]
MATERIALS
MATERIAL DESCRIPTION |  | DELIVERY LOCATION |  | COMPANY | QTY |  | UNITS |  | DOCKET NO | DELIVERY METHOD | CREW NO. | COST CODE | NOTES / COMMENTS
SUBCONTRACT SCOPE OF WORKS
WORK DESCRIPTION | EQUIPMENT DETAILS | PLANT REGO / INDUCTION NO | OPERATOR NAME | COMPANY | START | BREAK | FINISH | WORKED HRS | DOCKET NO | WORK QTY | UNIT | COST+A95:N110 CODE | NOTES / COMMENTS [NO OF LOADS, PER M3, PER TON, PER M ETC]
** end do no delete